## Plan
Project plan - website relaunch
Owner: Marketing team
ID | Task | Owner | Start | End | Status | Notes | Internal cost
T-001 | Kick-off workshop | Anna | 2026-01-05 | 2026-01-06 | Done | Agenda shared with all stakeholders in advance. | 1200
T-002 | Content inventory | Ben | 2026-01-07 | 2026-01-23 | Done |  | 3400
T-003 | Wireframes | Chloe | 2026-01-26 | 2026-02-13 | In progress | Mobile first. Needs sign-off by the brand team before visual design starts. | 5600
T-004 | Visual design | Chloe | 2026-02-16 | 2026-03-06 | Planned |  | 7800
T-005 | Old CMS migration | Dev team | 2026-02-02 | 2026-03-27 | Cancelled | Replaced by T-006. | 0
T-006 | Build in new CMS | Dev team | 2026-03-09 | 2026-04-24 | Planned |  | 18500
T-007 | Go-live | Anna | 2026-05-04 | 2026-05-04 | Planned |  | 900
Column C (Owner) is hidden. Row heights grow with wrapped notes.
| Right | Centre | Bold italic | Theme tint | Thick box